## Start Here
Microsoft 365 Cross-Tenant Mailbox Migration Tracker
Companion to the README runbook. Official reference: https://learn.microsoft.com/en-us/microsoft-365/migration/cross-tenant-mailbox-migration
How to use | Work through the sheets in order. Record each value as you complete the matching runbook step.
Yellow cells | Cells you fill in.
Grey cells | Formulas. Do not overwrite.
Blue cells | Example row or example value showing the expected format. Replace or delete it.
Never record secrets | Do not enter the client secret value, passwords or tokens anywhere in this file. Record only the expiry date and the name of the vault or store that holds the secret.
Sheet | Purpose
Summary | Live totals and progress (formulas).
Tenants | Source and target tenant details (Runbook Step 1).
App & Config | Migration app, endpoint, organisation relationships, scope group (Steps 3 and 4). Builds the consent URL.
Checklist | Every runbook step with status, owner, date and notes.
Users | One row per mailbox: source values, target MailUser values, automatic GUID checks, move and validation status (Steps 5 to 10).
Batches | Pilot and production batches (Steps 7 to 9).
Issues | Problems, causes and fixes (Troubleshooting, Step 11).

## Summary
Summary (all values are formulas)
Measure | Value
Mailboxes recorded | 1
Mailboxes on hold (blocked) | 0
ExchangeGuid mismatches | 0
ArchiveGuid mismatches | 0
Ready to migrate | 1
Not ready | 0
Moves completed | 0
Moves failed | 0
Moves completed (%) | 0%
Batches recorded | 1
Checklist items done | 0
Checklist items blocked | 0
Checklist progress (excluding N/A) | 0%
Open issues | 0
Client secret expiry date
Note: the example rows on Users, Batches and Issues are counted until you overwrite them.

## Tenants
Tenant details (Runbook Step 1)
Item | Source tenant | Target tenant | Example (format only)
Organisation name |  |  | Contoso Ltd
Tenant ID (GUID) |  |  | 11111111-2222-3333-4444-555555555555
Initial domain (onmicrosoft.com) |  |  | contoso.onmicrosoft.com
Custom domain(s) in use |  |  | contoso.com
Tenant admin contact |  |  | A. Admin, admin@contoso.com
Admin account used for PowerShell |  |  | migadmin@contoso.onmicrosoft.com
Cloud environment |  |  | Microsoft 365 commercial
Exchange Online provisioned (Yes/No) |  |  | Yes
Directory type (Cloud-only / Hybrid-synchronised) |  |  | Cloud-only
Cross Tenant User Data Migration licences purchased |  |  | 50
Domain move planned? (Yes/No) and date |  |  | Yes, 2026-11-20
Migration window |  |  | 2026-11-14 18:00 to 2026-11-15 06:00
Pilot group |  |  | 5 IT staff
Rollback decision recorded (Yes/No) and where |  |  | Yes, change ticket CHG-1042

## App & Config
Migration app, endpoint and organisation relationships (Runbook Steps 3 and 4)
Item | Value | Date done | Done by | Example (format only)
TARGET: App registration name |  |  |  | CrossTenantMailboxMigration
TARGET: Application (client) ID |  |  |  | aaaaaaaa-bbbb-cccc-dddd-eeeeeeeeeeee
TARGET: Redirect URI |  |  |  | https://office.com
TARGET: Permission added (Mailbox.Migration) |  |  |  | Yes
TARGET: Client secret expiry date |  |  |  | 2026-12-31
TARGET: Where the secret is stored (name only, never the value) |  |  |  | Company password vault, item 'XT-Migration'
TARGET: Admin consent granted in target |  |  |  | Yes
SOURCE: Admin consent accepted (consent URL below) |  |  |  | Yes
CONSENT URL (generated, send to source admin) | Fill in source initial domain (Tenants) and client ID (above) |  |  | https://login.microsoftonline.com/contoso.onmicrosoft.com/adminconsent?client_id=...&redirect_uri=https://office.com
TARGET: Migration endpoint name |  |  |  | CrossTenant-Source
TARGET: Endpoint remote server |  |  |  | outlook.office.com
TARGET: Endpoint created successfully |  |  |  | Yes
TARGET: Organisation relationship name |  |  |  | CrossTenant-Source
TARGET: Organisation relationship (Inbound) verified |  |  |  | Yes
SOURCE: Scope group name |  |  |  | CrossTenant-Migration-Scope
SOURCE: Organisation relationship name |  |  |  | CrossTenant-Target
SOURCE: Organisation relationship (RemoteOutbound) verified |  |  |  | Yes
SOURCE: Group membership checked against Users sheet |  |  |  | Yes
TARGET: Target delivery domain |  |  |  | fabrikam.onmicrosoft.com
Microsoft validation script run (date and result) |  |  |  | 2026-11-10, no issues
Test-MigrationServerAvailability result |  |  |  | Success

## Checklist
Runbook checklist
Step | Task | Status | Owner | Date | Notes / evidence | Dates: enter as yyyy-mm-dd
1 | Record tenant IDs, domains, admin contacts | Not started
1 | Confirm supported cloud environments and Exchange Online provisioned | Not started
1 | Cross Tenant User Data Migration licences assigned to each migrating user | Not started
1 | Target users have an appropriate Exchange Online licence plan | Not started
1 | Mailbox inventory completed (Users sheet) | Not started
1 | Holds checked; any holds resolved with legal/compliance approval | Not started
1 | Target UPN and SMTP domain decided; domain move planned | Not started
1 | Pilot group and migration window agreed; users notified | Not started
1 | Rollback decision recorded | Not started
2 | ExchangeOnlineManagement module installed/updated | Not started
2 | Execution policy checked | Not started
2 | Connected to correct tenant (verified with Get-OrganizationConfig) | Not started
3 | App registered in target Entra (multitenant, redirect https://office.com) | Not started
3 | Mailbox.Migration application permission added | Not started
3 | Client secret created and stored securely; expiry recorded | Not started
3 | Admin consent granted in target | Not started
3 | Consent URL sent to source admin and accepted | Not started
3 | Migration endpoint created in target | Not started
3 | Organisation relationship created in target (Inbound) | Not started
4 | Source consent verified in Enterprise applications | Not started
4 | Mail-enabled security scope group created in source | Not started
4 | Scope group membership matches approved users | Not started
4 | Source organisation relationship created (RemoteOutbound, app ID, scope) | Not started
5 | Source mailbox details exported (GUIDs, LegacyExchangeDN, X500) | Not started
5 | Target MailUsers created | Not started
5 | ExchangeGUID, ArchiveGUID and X500 addresses stamped | Not started
5 | Primary SMTP and ExternalEmailAddress set | Not started
5 | MailUser values verified before licensing (Users sheet checks show OK) | Not started
5 | Exchange and Cross Tenant licences assigned after verification | Not started
6 | Get-MigrationEndpoint and Test-MigrationServerAvailability succeed | Not started
6 | Microsoft validation script run; all issues fixed | Not started
7 | users.csv created with target addresses; copy kept | Not started
8 | Pilot batch created (not started) and inspected | Not started
8 | Pilot batch started and completed | Not started
8 | Pilot validated and signed off | Not started
9 | Production batches scheduled; delegates grouped together | Not started
9 | Production batches completed | Not started
10 | Mail content verified (counts, date ranges, archive) | Not started
10 | Inbound and outbound mail tested | Not started
10 | Outlook web, desktop and mobile sign-in tested | Not started
10 | Delegates, shared mailboxes, rules, forwarding and calendar sharing recreated | Not started
10 | Teams meetings recreated where needed | Not started
10 | Hybrid objects and targetAddress updated (if applicable) | Not started
10 | Compliance owner confirmed retention, eDiscovery and audit | Not started
10 | Business owner sign-off obtained | Not started
12 | Reports and change records retained | Not started
12 | Endpoint and organisation relationships removed (only if no further moves) | Not started
12 | App secret rotated/removed; app and consent removed | Not started
12 | Source MailUsers and routing reviewed | Not started
12 | Documentation and support runbooks updated | Not started

## Users
Mailbox map (Runbook Steps 5 to 10)
Row 5 is an example (blue). Overwrite it with your first user. Grey columns are automatic checks.
# | Display name | Source UPN | Source primary SMTP | Source routing address (onmicrosoft.com) | Source ExchangeGuid | Source ArchiveGuid | Archive? (Yes/No) | Source LegacyExchangeDN | Source X500 addresses (; separated) | Mailbox size (GB) | On any hold? (Yes/No) | Delegates / shared mailbox links | Target UPN | Target primary SMTP | Target MailUser ExchangeGuid | Target MailUser ArchiveGuid | Exchange licence assigned (Yes/No) | Cross Tenant licence assigned (Yes/No) | ExchangeGuid check | ArchiveGuid check | Ready to migrate? | Batch name | Move status | Mail flow tested | Outlook tested | Delegates recreated | Notes
1 | Alex Example | alex@contoso.com | alex@contoso.com | alex@contoso.onmicrosoft.com | 0a1b2c3d-1111-2222-3333-444455556666 | 9f8e7d6c-aaaa-bbbb-cccc-ddddeeeeffff | Yes | /o=ExchangeLabs/ou=Exchange Administrative Group (FYDIBOHF23SPDLT)/cn=Recipients/cn=EXAMPLE-alex | x500:/o=OldOrg/ou=First Administrative Group/cn=Recipients/cn=alex | 12.4 | No | None | alex@fabrikam.com | alex@fabrikam.com | 0a1b2c3d-1111-2222-3333-444455556666 | 9f8e7d6c-aaaa-bbbb-cccc-ddddeeeeffff | Yes | Yes | OK | OK | Ready | CrossTenant-Pilot-2026-11-14 | Not started
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Batches
Migration batches (Runbook Steps 7 to 9)
Row 4 is an example (blue). Overwrite it with your pilot batch.
Batch name | Type | CSV file name | Users in batch (auto) | Created | Started | Completed | Status | Synced | Failed | Reports saved? (Yes/No) | Approved by | Notes
CrossTenant-Pilot-2026-11-14 | Pilot | users-pilot.csv | 1 | 2026-11-12 | 2026-11-14 | 2026-11-14 | Completed | 5 | 0 | Yes | J. Manager | Pilot signed off

## Issues
Issues log
Row 4 is an example (blue). Overwrite it with your first issue.
ID | Date | Step | Mailbox / area | Description | Error text / cmdlet | Cause | Action taken | Owner | Status | Resolved date
1 | 2026-11-12 | 5 | alex@fabrikam.com | Move failed on pilot mailbox | ExchangeGuid mismatch in migration report | Exchange licence assigned before GUID was stamped | Compared GUIDs; corrected via supported Microsoft procedure; no clearing of previous mailbox info | A. Admin | Resolved | 2026-11-13
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50