## Read Me
Microsoft 365 Cross-Tenant Migration — Information & Runbook Tracker
Purpose | Capture discovery, ownership, readiness, execution, validation and sign-off information for a Microsoft 365 tenant-to-tenant migration.
How to use
1 | Create one row per object/item in the relevant worksheet. Use unique IDs where possible.
2 | Replace example values and mark fields N/A only when the reason is recorded.
3 | Use the Status / Readiness dropdowns to track progress. Filter tables by owner, wave, status or blocker.
4 | Record decisions, exceptions and evidence links; avoid putting passwords, tokens, recovery codes or other secrets in this workbook.
5 | Confirm the migration method and scope against current Microsoft documentation and your tenant/licensing constraints.
6 | Use the Cutover Checklist for go/no-go decisions and post-migration validation. Keep a separate rollback plan and change record.
Key references
Microsoft 365 cross-tenant mailbox migration | https://learn.microsoft.com/en-us/microsoft-365/enterprise/cross-tenant-mailbox-migration
Cross-tenant OneDrive migration | https://learn.microsoft.com/en-us/sharepointmigration/cross-tenant-onedrive-migration
Microsoft 365 tenant-to-tenant migration overview (planning starting point) | https://learn.microsoft.com/en-us/microsoft-365/enterprise/
Project details
Project / Change ID
Source tenant name
Source tenant ID
Target tenant name
Target tenant ID
Migration lead
Technical lead
Business owner
Planned migration window
Timezone
Change ticket / CAB ref

## Users & Workloads
Use one row per user or workload owner record; split into separate rows if different workloads need separate tracking.
Record ID | Migration Wave | Object Type | Display Name | Source UPN / Identity | Target UPN / Identity | Source Object ID | Target Object ID | Department / Business Unit | Business Owner | Technical Owner | Workload(s) in Scope | License / SKU Notes | Mailbox Size / Item Count | OneDrive Size / Status | Teams / Groups Dependencies | Source Sign-in / Account State | Target Account Prepared? | Pre-check Result | Migration Status | Validation Result | Exception / Blocker | Evidence / Ticket Link | Notes

## Tenant Readiness
Record tenant-level configuration, identity, DNS, security and migration prerequisites. Confirm applicable checks for your selected migration method.
ID | Area | Check / Required Information | Source Tenant Value / Result | Target Tenant Value / Result | Owner | Status | Dependency / Prerequisite | Risk if incomplete | Evidence / Link | Last Checked | Notes
TR-01 | Tenant identity | Tenant name, tenant ID, verified domains |  |  |  | Not started
TR-02 | Admin access | Authorized admin accounts and required roles verified (no credentials stored here) |  |  |  | Not started
TR-03 | Cross-tenant trust / app | Migration application, consent and required permissions configured per chosen method |  |  |  | Not started
TR-04 | Licensing | Required licenses, migration licenses and target workload licenses confirmed |  |  |  | Not started
TR-05 | Domains / UPN | Domain ownership, UPN mapping and domain move/retention plan confirmed |  |  |  | Not started
TR-06 | Identity | Entra ID users, groups, guests and identity mapping reviewed |  |  |  | Not started
TR-07 | Authentication | MFA, Conditional Access, SSO and authentication impact assessed |  |  |  | Not started
TR-08 | Mail flow | Accepted domains, connectors, transport rules, forwarding and mail routing reviewed |  |  |  | Not started
TR-09 | DNS | MX, Autodiscover, SPF, DKIM, DMARC and other relevant DNS change plan documented |  |  |  | Not started
TR-10 | Exchange | Mailbox types, archive, delegates, permissions, retention and holds assessed |  |  |  | Not started
TR-11 | SharePoint / OneDrive | Sites, sharing links, permissions, storage and external access assessed |  |  |  | Not started
TR-12 | Teams | Teams, channels, meetings, apps, policies, phone/voice and dependencies assessed |  |  |  | Not started
TR-13 | Compliance | Purview retention, eDiscovery, sensitivity labels, DLP and audit requirements reviewed |  |  |  | Not started
TR-14 | Devices / apps | Intune, enrollment, Office apps, mobile devices and enterprise apps impact reviewed |  |  |  | Not started
TR-15 | Monitoring | Monitoring, alerting, support escalation and service health checks prepared |  |  |  | Not started
TR-16 | Change control | Change approval, communications, maintenance window and stakeholder sign-off recorded |  |  |  | Not started

## Exchange Mailboxes
Capture mailbox-specific dependencies and validation. Confirm supported mailbox types, hold/retention constraints and exact prerequisites in Microsoft documentation.
Record ID | Wave | Mailbox Type | Display Name | Source Primary SMTP | Target Primary SMTP | Source UPN | Mailbox Size | Archive? | Litigation / In-Place Hold? | Retention / Compliance Notes | Delegates / Permissions | Send As / Send on Behalf | Forwarding / Rules | Shared Mailbox Access | Migration Batch / Job | Pre-check | Migration Status | Post-check: Mail Flow | Post-check: Calendar / Delegates | Post-check: Outlook / Mobile | Owner | Ticket / Evidence | Notes

## Files & SharePoint
Use one row per OneDrive account, SharePoint site or content unit. SharePoint/OneDrive migration scope and supported content can vary by method.
Record ID | Workload | Source User / Site | Source URL / Identifier | Target User / Site | Target URL / Identifier | Content Owner | Size / Item Count | Permissions / Sharing Review | External Sharing Required? | Known Link Dependencies | Versioning / Metadata Requirements | Retention / Sensitivity Labels | Pre-check | Migration Job / Batch | Migration Status | Post-check: Content | Post-check: Permissions | Post-check: Sharing Links | Issue / Exception | Evidence / Ticket Link | Notes

## Teams & Groups
Track Teams, Microsoft 365 groups and collaboration dependencies separately; do not assume every Teams component migrates with mailbox or OneDrive data.
Record ID | Object Type | Team / Group Name | Source ID / URL | Target ID / URL | Owner | Members / Owners Exported? | Channels / Private Channels | Apps / Tabs / Connectors | Meetings / Calendar Impact | Voice / Phone Dependencies | Files Location | Migration Approach / Tool | Pre-check | Status | Post-check: Membership | Post-check: Files | Post-check: Apps / Tabs | User Communication | Issue / Exception | Evidence / Ticket Link | Notes

## Apps & Devices
Capture Entra applications, SSO, automation, integrations, devices and service dependencies. Never record actual passwords, client secrets, certificates' private keys or tokens.
Record ID | Category | Application / Device / Integration | Business Purpose | Business Owner | Technical Owner | Source Tenant Dependency | Target Tenant Action | Authentication / SSO | Permissions / API Consent | Certificates / Secrets Owner (no secret values) | Device / Enrollment Impact | Testing Plan | Status | Test Result | Cutover Required? | Rollback / Workaround | Ticket / Evidence Link | Notes

## Cutover Checklist
Tailor this checklist to the approved migration design. Dates/times should include timezone in the cell or notes.
Step ID | Phase | Activity / Check | Acceptance Criteria / Evidence | Owner | Planned Date / Time | Actual Date / Time | Status | Go/No-Go Impact | Dependency | Issue / Decision Log | Evidence / Ticket Link | Notes
CO-01 | Plan | Scope and migration waves frozen | Approved inventory and exclusions recorded |  |  |  | Not started | Go/No-Go
CO-02 | Plan | Stakeholders and support rota confirmed | Business, IT, service desk and escalation contacts confirmed |  |  |  | Not started | Go/No-Go
CO-03 | Plan | Backup/export and rollback/recovery plan reviewed | Recovery steps, owners and decision trigger documented |  |  |  | Not started | Go/No-Go
CO-04 | Readiness | Source/target tenant prerequisites validated | Required access, licensing, permissions and configuration checked |  |  |  | Not started | Go/No-Go
CO-05 | Readiness | Pilot completed and signed off | Representative pilot users/workloads pass agreed tests |  |  |  | Not started | Go/No-Go
CO-06 | Readiness | Communications sent | Users know timing, expected impact and support route |  |  |  | Not started | Go/No-Go
CO-07 | Cutover | Change approval / CAB confirmed | Approved change record and maintenance window |  |  |  | Not started | Go/No-Go
CO-08 | Cutover | DNS / domain / mail-flow changes executed if applicable | Changes verified against approved plan |  |  |  | Not started | Go/No-Go
CO-09 | Migration | Migration jobs/batches started | Job IDs and start times recorded |  |  |  | Not started | Monitor
CO-10 | Migration | Migration jobs/batches completed | Errors reviewed; failed items remediated or accepted |  |  |  | Not started | Monitor
CO-11 | Validation | Mailbox access and mail flow tested | Send/receive, calendar and delegated access tests pass |  |  |  | Not started | Go/No-Go
CO-12 | Validation | OneDrive / SharePoint access tested | Content, permissions and required sharing access pass |  |  |  | Not started | Go/No-Go
CO-13 | Validation | Teams / groups / apps tested | In-scope collaboration and app scenarios pass |  |  |  | Not started | Go/No-Go
CO-14 | Validation | Security and compliance checks completed | Access policies, labels, retention and audit needs verified |  |  |  | Not started | Go/No-Go
CO-15 | Support | Service desk briefed and monitoring active | Known issues, escalation and service checks in place |  |  |  | Not started | Monitor
CO-16 | Close | Business owner sign-off captured | Acceptance, open issues and residual risks acknowledged |  |  |  | Not started | Close
CO-17 | Close | Lessons learned and documentation updated | Runbook, inventory and exception log updated |  |  |  | Not started | Close

## Risks & Decisions
Use this log for risks, assumptions, issues, dependencies and decisions. Link to the formal change/risk system where one exists.
ID | Type | Date Raised | Description | Impact | Likelihood | Severity / Priority | Mitigation / Decision | Owner | Due Date | Status | Related Workload / Wave | Approver | Evidence / Ticket Link | Closure Notes

## Comms & Sign-off
Record communication milestones and explicit approvals. Do not treat a sent message as business sign-off unless that is the agreed process.
ID | Audience / Stakeholder | Communication / Approval | Owner | Planned Date | Actual Date | Channel | Status | Approver / Recipient | Decision / Feedback | Evidence / Link | Notes